Northeast Minnesota Continuum of Care

2021 HUD CoC NOFA Schedule

**Please check for updates/changes to this schedule. Updates made following the original posting of this document will be made in red.**

|  |  |
| --- | --- |
| Date |  |
| June 16, 2021 | NE CoC Performance and Evaluation Committee meeting to review Ranking Tool; develop recommended Ranking Procedure to CoC. |
| Date TBD: June - July | HUD releases CoC Notice of Funding Availability (NOFA) (RFP). |
| Date TBD (within one week of HUD releasing the NOFA) | CoC email and website posting to announce NOFA availability |
| Date TBD | E-SNAPS opens (<https://www.hudexchange.info/programs/e-snaps/>) |
| Date TBD | Priorities and Processes of FY 2021 Continuum of Care (CoC) Program Competition NOFA Webinar |
| **Week of July 12, 2021** | **Intent to Apply and Threshold form and supplemental documents distributed via email and posted on the CoC website.** Renewal projects that intend to voluntarily reallocate some or all of their funding are strongly encouraged to contact their CoC Co-Coordinators as soon as possible. |
| July 19, 2021 | Performance and Evaluation Committee meets to finalize scoring criteria recommendation to the board |
| **July 27, 2021** | **First round of New Project Applicants: Intent to Apply and Threshold forms due to CoC via email to** [**clundquist@live.com**](mailto:clundquist@live.com) **(Cara Lundquist, CoC Co-Coordinator)** |
| **July 27, 2021** | **Renewal Project Applicants: Intent to Apply and Threshold forms, Financial Assessment Forms, and Project HMIS APRs (01/01/2020 – 12/31/2020) due to CoC via email to** [**clundquist@live.com**](mailto:clundquist@live.com) **(Cara Lundquist, CoC Co-Coordinator).** |
| Week of July 26, 2021 | Ranking and Review Committee meets to review Renewal project Intent to Apply Forms and Supplemental Application materials to determine if projects meet eligibility to apply and to identify any recommendations to reallocate CoC project funding. |
| Week of August 2, 2021 | Announcements of available reallocation funding and call for new project applications distributed via email and posted on the NE CoC website. |
| Week of August 2, 2021 | Project applicants meeting criteria on the Intent to Apply and Threshold form invited to apply for full project application |
| Week of August 9, 2021 | NE CoC Governing Board Special Meeting via Zoom to review and approve scoring criteria. *Reminder: All CoC meetings are open to the public.* *Please email Cara Lundquist (*[*clundquist@live.com*](mailto:clundquist@live.com)*) for Zoom information.* |
| Date TBD  Late July – Early August | Project Applicant LAB for NE CoC (Work on Applications)  *Project Applicants should begin their application draft prior to this lab.* |
| **August 11, 2021** | **Final round of New Project Applicants: Intent to Apply and Threshold forms due to CoC via email to** [**clundquist@live.com**](mailto:clundquist@live.com) **(Cara Lundquist, CoC Co-Coordinator)** |
| **August 20, 2021** | **In order to be considered for the 2021 competition, project applications should be entered in ESnaps and a PDF copy sent to Cara Lundquist via email (clundquist@live.com)** |
| **August 20, 2021** | **Project application supplemental documents submitted to Cara Lundquist via email (**[**clundquist@live.com**](mailto:clundquist@live.com)**)** |
| Week of August 23, 2021 | Ranking and Review Committee meets to review, score and rank applications. |
| TBD – Week of August 30, 2021 | Project Applicants notified in writing by the Review and Ranking Committee if their project was reduced or rejected. |
| TBD – Week of August 30, 2021 | Project Applicants notified in writing by the Review and Ranking Committee if their project was accepted and ranked on the Priority Listing. |
| **TBD – 1 week after notifications are distributed** | **Appeals due to Ranking and Review Committee** |
| **TBD – HUD deadline** | **Project Applicants submit final applications in e-snaps.** |
| September 9, 2021 | Ranking and Review Committee meets via Zoom to review and take action on Appeals (if any). |
| September 9, 2021 | NE CoC Governing Board Meeting from 10:00am – 12:00pm (location TBD). Vote to Approve Project Listing.  NE CoC Governance Committee meets to review and provide feedback to Collaborative Application. |
| TBD September 2021 | Preliminary Project Listing submitted in E-snaps by Patty and Cara (CoC Co-Coordinators) |
| TBD September 2021 (two weeks prior to submission) | Final rankings posted on e-snaps, draft Collaborative Application and all other NOFA materials posted on CoC website for public review. CoC notified via email of availability. |
| TBD September 2021 | NE CoC reviews and sends feedback via CoC website or email on Collaborative Application. |
| TBD September 2021 | NE CoC Governing Board vote to approve final Collaborative Application. |
| TBD September 2021 | Final Collaborative Application and Project Listing submitted in E-snaps. |
| TBD September 2021 | Final Collaborative Application and Project Listing posted on CoC website for public review. CoC notified via email of availability. |
| **TBD** | **HUD DEADLINE for Consolidated Application with project priority list, project applications, and all attachments.** |